## pmc04_cluster_profile_status_01
MSB-PMC04 Promox Cluster.
(all integers are GigaBytes)
1 Cluster supporting Development and Production Cluster
All NODES in VLAN37
Development Cluster
Node | Racked? | Ram | ZFS | OSD | OSD | OSD Totals | PubIP | iLOs | TO DO | TO DO | TO DO | TO DO | TO DO
msb-pmc04-01 | Yes | 160GB | 3x600GB | 5x1200GB |  | 6000 | Not Yet Assigned | 10.1.32.162 | Austin: install 10/25 fibre, cable, test | Sean: Assign Public Ips to 10/25 interface |  |  | Rohn: Label
msb-pmc04-02 | Yes | 160GB | 3x600GB | 3x1200GB | 5x900GB | 8100 | Not Yet Assigned | 10.1.32.199 | Austin: install 10/25 fibre, cable, test | Sean: Assign Public Ips to 10/25 interface |  |  | Rohn: Label
msb-pmc04-03 | Yes | 160GB | 3x600GB | 5x1200GB |  | 6000 | Not Yet Assigned | 10.1.32.172 | Austin: install 10/25 fibre, cable, test | Sean: Assign Public Ips to 10/25 interface |  |  | Rohn: Label
msb-pmc04-04 | Yes | 160GB | 3x600GB | 3x1200GB | 5x900GB | 8100 | Not Yet Assigned | 10.1.32.232 | Austin: install 10/25 fibre, cable, test | Sean: Assign Public Ips to 10/25 interface |  |  | Rohn: Label
Production Cluster
Node | Racked? | Ram | ZFS | OSD | OSD | OSD Totals | PubIP | iLOs | TO DO |  | TO DO | TO DO | TO DO
msb-pmc04-05 | Yes | 96GB | 3x600GB | 21x1200GB |  | 25200 | Not Yet Assigned |  | Sean: install 10/25 fibre, cable, test; | Sean: Assign Public Ips to 10/25 interface | Rohn: install 1.2TB drive | Sean: Configure ILO | Rohn: Label
msb-pmc04-06 | Yes | 128gb | 3x300GB | 17x1200GB | 4x900GB | 21300 | 10.1.37.58 | 10.1.32.58 | Sean: install 10/25 fibre, cable, test |  | Rohn: install 3x900GB drives |  | Rohn: Label